## ZFJ-Cycles-05-06-2022
ExecutionId | CycleName | Issue Key | Test Summary | OrderId | Step | Test Data | Expected Result | Step Result | Project | Priority | Executed By | Executed On | ExecutionStatus | ExecutionDefects | CreationDate | StepId
2fbf22fa-c2d9-48c3-8195-82ca1288f9b9 | Test proiect final | DAN-2 | [Work Experience page] Verify how many Work Experience records can be added | 1 | Login to Orange HRM. | Credentials used: Admin/admin123 | The user can successfully login into the application. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:05 | PASS |  | 2022-04-05 09:37 | 0d90e186-9400-409e-9880-70f331875f7f
2fbf22fa-c2d9-48c3-8195-82ca1288f9b9 | Test proiect final | DAN-2 | [Work Experience page] Verify how many Work Experience records can be added | 2 | Access My Info module and open the Qualifications section. | https://opensource-demo.orangehrmlive.com/index.php/pim/viewQualifications/empNumber/7 | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:05 | PASS |  | 2022-04-05 09:37 | 34024214-6310-4b9c-abb8-dbc627a72ca1
2fbf22fa-c2d9-48c3-8195-82ca1288f9b9 | Test proiect final | DAN-2 | [Work Experience page] Verify how many Work Experience records can be added | 3 | Click on Add Work Experience. |  | The work Experience entry is opened successfully. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:05 | PASS |  | 2022-04-05 09:37 | a954e85b-cf80-4799-8dab-77ab9d47b8ff
2fbf22fa-c2d9-48c3-8195-82ca1288f9b9 | Test proiect final | DAN-2 | [Work Experience page] Verify how many Work Experience records can be added | 4 | Fill in all the mandatory information. | Company Job Title | All mandatory fields are completed. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:05 | PASS |  | 2022-04-05 09:37 | e0b9357a-7ccf-4858-b2e8-e6f9fc5b7b8f
2fbf22fa-c2d9-48c3-8195-82ca1288f9b9 | Test proiect final | DAN-2 | [Work Experience page] Verify how many Work Experience records can be added | 5 | Click on the Save button. | https://opensource-demo.orangehrmlive.com/index.php/pim/viewQualifications/empNumber/7#workexperience | The Work Experience entry is closed and the name is saved successfully. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:05 | PASS |  | 2022-04-05 09:37 | b6777600-17bb-4506-beb1-989849f20821
2fbf22fa-c2d9-48c3-8195-82ca1288f9b9 | Test proiect final | DAN-2 | [Work Experience page] Verify how many Work Experience records can be added | 6 | Add 20 records. |  | The user can add as many entries as he wants. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:05 | PASS |  | 2022-04-05 09:37 | 4ddb0e7f-2ebe-4efb-a115-44f8d054e1a1
b69de4e7-a21a-4d88-8042-201be4dae3eb | Test proiect final | DAN-3 | [Save Button] Verify that user can save information after Work Experience record is updated | 1 | Precondition: at least one Work Experience registered. |  |  | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:18 | PASS |  | 2022-04-05 09:37 | 1748d1f6-e120-43cd-a761-bea8c2a3f626
b69de4e7-a21a-4d88-8042-201be4dae3eb | Test proiect final | DAN-3 | [Save Button] Verify that user can save information after Work Experience record is updated | 2 | Login to Orange HRM. | https://opensourcedemo. orangehrmlive.com/ Credentials used: Admin/admin123 | The user is successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:18 | PASS |  | 2022-04-05 09:37 | 16e1ed41-3c81-4f57-93a3-6c76675fb8e0
b69de4e7-a21a-4d88-8042-201be4dae3eb | Test proiect final | DAN-3 | [Save Button] Verify that user can save information after Work Experience record is updated | 3 | Access My Info module and open the Qualifications section. | https://opensource-demo.orangehrmlive.com/index.php/pim/viewQualifications/empNumber/7 | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:18 | PASS |  | 2022-04-05 09:37 | 5d49dc01-3592-4302-87cc-e276c5dce695
b69de4e7-a21a-4d88-8042-201be4dae3eb | Test proiect final | DAN-3 | [Save Button] Verify that user can save information after Work Experience record is updated | 4 | Click on the name of the Company you want to change. | Company | The Work Experience entry is opened successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:18 | PASS |  | 2022-04-05 09:37 | 5b4fe664-fbaa-4286-bbb7-8ebadb21712d
b69de4e7-a21a-4d88-8042-201be4dae3eb | Test proiect final | DAN-3 | [Save Button] Verify that user can save information after Work Experience record is updated | 5 | Change values for one or many fields and press Save button. | Company Job Title From - To Comment | The Work Experience edit form is closed and all changes are done successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:18 | PASS |  | 2022-04-05 09:37 | 39d330d9-c7ee-4736-b538-2a0663ddaf77
b69de4e7-a21a-4d88-8042-201be4dae3eb | Test proiect final | DAN-3 | [Save Button] Verify that user can save information after Work Experience record is updated | 6 | Click on the name of the Company again. | Company | The Work Experience entry is opened successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:18 | PASS |  | 2022-04-05 09:37 | 7a28e867-0132-4b3b-844d-bc31f84cc0aa
b69de4e7-a21a-4d88-8042-201be4dae3eb | Test proiect final | DAN-3 | [Save Button] Verify that user can save information after Work Experience record is updated | 7 | Don't change anything and press Save button. |  | The Work Experience edit form is closed and the information remains the same. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:18 | PASS |  | 2022-04-05 09:37 | 6bb26464-896c-40fc-b237-966ad219f910
739ec6a5-88a1-4c2e-b2bb-5e95fe5c3230 | Test proiect final | DAN-6 | [Cancel Button] Verify that user can cancel action when edit Work Experience record | 1 | Precondition: at least one Work Experiences entry added before. |  |  | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:24 | PASS |  | 2022-04-05 09:37 | b9f6807b-4f26-44c8-91d2-1aa8e3546fb7
739ec6a5-88a1-4c2e-b2bb-5e95fe5c3230 | Test proiect final | DAN-6 | [Cancel Button] Verify that user can cancel action when edit Work Experience record | 2 | Login to Orange HRM. | https://opensource-demo.orangehrmlive.com | The user is successfully login into the application | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:24 | PASS |  | 2022-04-05 09:37 | 3afbae5e-8c6f-4ddc-a7cc-8d75b459487f
739ec6a5-88a1-4c2e-b2bb-5e95fe5c3230 | Test proiect final | DAN-6 | [Cancel Button] Verify that user can cancel action when edit Work Experience record | 3 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:24 | PASS |  | 2022-04-05 09:37 | 24b8e351-03d0-49ec-a99f-afc3bb72079f
739ec6a5-88a1-4c2e-b2bb-5e95fe5c3230 | Test proiect final | DAN-6 | [Cancel Button] Verify that user can cancel action when edit Work Experience record | 4 | Acces Work Experience section by selecting one entry from the assigned list, clicking on the name of the company. |  | The Work Experience entry is opened successfully. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:24 | PASS |  | 2022-04-05 09:37 | 634f4f8e-f01e-417f-8e28-9ea42227c271
739ec6a5-88a1-4c2e-b2bb-5e95fe5c3230 | Test proiect final | DAN-6 | [Cancel Button] Verify that user can cancel action when edit Work Experience record | 5 | Change values for one or many fields and press Cancel button. |  | The Work Experience edit form is closed and no changes were done. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:24 | PASS |  | 2022-04-05 09:37 | 933016ec-da66-45a3-ab5f-0ec0208c1415
739ec6a5-88a1-4c2e-b2bb-5e95fe5c3230 | Test proiect final | DAN-6 | [Cancel Button] Verify that user can cancel action when edit Work Experience record | 6 | Acces Work Experience section by selecting the same entry from the assigned list, clicking on the name of the company. |  | The Work Experience entry is opened successfully. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:24 | PASS |  | 2022-04-05 09:37 | d431a4e4-6baa-4203-bed9-0b87b7ed6d92
739ec6a5-88a1-4c2e-b2bb-5e95fe5c3230 | Test proiect final | DAN-6 | [Cancel Button] Verify that user can cancel action when edit Work Experience record | 7 | Don't change anything and press Cancel button. |  | The Work Experience edit form is closed and the information remains the same. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:24 | PASS |  | 2022-04-05 09:37 | 102dd58b-1686-437e-ab8e-71f472f5c93b
9b18f057-b740-4fce-81a0-131c6392fc5a | Test proiect final | DAN-7 | [Cancel Button] Verifiy that user can cancel action when all fields are completed | 1 | Login to Orange HRM. | https://opensource-demo.orangehrmlive.com | The user is successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:26 | PASS |  | 2022-04-05 09:37 | 3387cd4e-c27c-4ec2-b7db-893899966024
9b18f057-b740-4fce-81a0-131c6392fc5a | Test proiect final | DAN-7 | [Cancel Button] Verifiy that user can cancel action when all fields are completed | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:26 | PASS |  | 2022-04-05 09:37 | c4083409-1953-44eb-a0cc-d87187f4033e
9b18f057-b740-4fce-81a0-131c6392fc5a | Test proiect final | DAN-7 | [Cancel Button] Verifiy that user can cancel action when all fields are completed | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:26 | PASS |  | 2022-04-05 09:37 | fbf21c70-6baa-4be0-9693-de6db9258f59
9b18f057-b740-4fce-81a0-131c6392fc5a | Test proiect final | DAN-7 | [Cancel Button] Verifiy that user can cancel action when all fields are completed | 4 | Fill in all mandatory fields | Company Job Title | All mandatory fields are filled in. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:26 | PASS |  | 2022-04-05 09:37 | 29b7915a-f240-4f16-9441-bead8037f313
9b18f057-b740-4fce-81a0-131c6392fc5a | Test proiect final | DAN-7 | [Cancel Button] Verifiy that user can cancel action when all fields are completed | 5 | Press cancel button. |  | Add Work Experience section is closed without changes into the list. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:26 | PASS |  | 2022-04-05 09:37 | 329a3767-03f5-4bb0-9719-91c057ea8942
2fbdde36-3a8f-421c-87d8-e96db9a58be8 | Test proiect final | DAN-4 | [Save Button] Verify that user can't save action when no field was fill in | 1 | Login to Orange HRM. | https://opensource-demo.orangehrmlive.com/ Credentials used: Admin/admin123 | The user can successfully login into the application. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:21 | PASS |  | 2022-04-05 09:37 | 3a2bb5da-7935-4ee8-8339-3f3f2e2617ac
2fbdde36-3a8f-421c-87d8-e96db9a58be8 | Test proiect final | DAN-4 | [Save Button] Verify that user can't save action when no field was fill in | 2 | Access My Info module and open the Qualifications section. | https://opensource-demo.orangehrmlive.com/index.php/pim/viewQualifications/empNumber/7 | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:21 | PASS |  | 2022-04-05 09:37 | 84b6d0ef-50d0-495c-926b-8c2468246fca
2fbdde36-3a8f-421c-87d8-e96db9a58be8 | Test proiect final | DAN-4 | [Save Button] Verify that user can't save action when no field was fill in | 3 | Click Add button in Work Experience section. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:21 | PASS |  | 2022-04-05 09:37 | f690b47d-6708-4db8-a0fb-2ad77cea8eac
2fbdde36-3a8f-421c-87d8-e96db9a58be8 | Test proiect final | DAN-4 | [Save Button] Verify that user can't save action when no field was fill in | 4 | Press Save button after no field is fill in. |  | Mandatory fields are required. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:21 | PASS |  | 2022-04-05 09:37 | 5c146f71-5a6b-46da-bc13-052f1ed41730
1633fd6e-9904-451a-959f-5dc733780f74 | Test proiect final | DAN-5 | [Delete button] Verify that many Work Experience entries can be deleted | 1 | Precondition: many Work Experiences entries added before. |  |  | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:23 | PASS |  | 2022-04-05 09:37 | 4ebe992f-f375-45c8-a2ae-1ef5e919086b
1633fd6e-9904-451a-959f-5dc733780f74 | Test proiect final | DAN-5 | [Delete button] Verify that many Work Experience entries can be deleted | 2 | Login to Orange HRM. | https://opensource-demo.orangehrmlive.com Credentials used: Admin/admin123 | The user is successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:23 | PASS |  | 2022-04-05 09:37 | 34c7eb3b-3f83-4017-a430-4fd5787fe1d6
1633fd6e-9904-451a-959f-5dc733780f74 | Test proiect final | DAN-5 | [Delete button] Verify that many Work Experience entries can be deleted | 3 | Access My Info module and open the Qualifications section. | https://opensource-demo.orangehrmlive.com/index.php/pim/viewQualifications/empNumber/7 | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:23 | PASS |  | 2022-04-05 09:37 | e9b060b5-f79c-474a-b793-86861d417da1
1633fd6e-9904-451a-959f-5dc733780f74 | Test proiect final | DAN-5 | [Delete button] Verify that many Work Experience entries can be deleted | 4 | Acces Work Experience section by selecting many entries from the assigned list, clicking on the check boxes, next to the names of the companies. | check boxes | The Work Experience entries are selected. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:23 | PASS |  | 2022-04-05 09:37 | 9359a115-1819-49b4-bf84-37c73dfe930e
1633fd6e-9904-451a-959f-5dc733780f74 | Test proiect final | DAN-5 | [Delete button] Verify that many Work Experience entries can be deleted | 5 | Click Delete button. |  | The selected Work Experience records are deleted successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:23 | PASS |  | 2022-04-05 09:37 | ee76f6f2-66da-4a3a-91a1-2140fc32c4d3
132d5f48-7b34-4277-bb78-9ab746e6ce5c | Test proiect final | DAN-8 | [Cancel Button] Verify that user can cancel action when no field was fill in | 1 | Login to Orange HRM. | https://opensource-demo.orangehrmlive.com | The user is successfully login into the application. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:27 | PASS |  | 2022-04-05 09:37 | 4bd94f1e-8cd6-4d23-9613-d0c3323bada2
132d5f48-7b34-4277-bb78-9ab746e6ce5c | Test proiect final | DAN-8 | [Cancel Button] Verify that user can cancel action when no field was fill in | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:27 | PASS |  | 2022-04-05 09:37 | eccc3f09-2f57-47b4-a9f0-6ec7838e6700
132d5f48-7b34-4277-bb78-9ab746e6ce5c | Test proiect final | DAN-8 | [Cancel Button] Verify that user can cancel action when no field was fill in | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:27 | PASS |  | 2022-04-05 09:37 | 3fc52d9b-8cb4-47cb-8727-b30c20ed5c1c
132d5f48-7b34-4277-bb78-9ab746e6ce5c | Test proiect final | DAN-8 | [Cancel Button] Verify that user can cancel action when no field was fill in | 4 | Press Cancel button. |  | Add Work Experience section is closed without any changes into the list. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 10:27 | PASS |  | 2022-04-05 09:37 | 105aadb3-8011-42a7-8e3e-62455bc987f9
9a0ce60c-c61b-4140-9807-c4dbeb401ca8 | Test proiect final | DAN-9 | [Company field] Verify that Company field is mandatory | 1 | Login to Orange HRM. | https://opensource-demo.orangehrmlive.com | The user can successfully login into the application. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 10:30 | PASS |  | 2022-04-05 09:37 | 37d624d0-1336-4437-aa5a-9533ddf11008
9a0ce60c-c61b-4140-9807-c4dbeb401ca8 | Test proiect final | DAN-9 | [Company field] Verify that Company field is mandatory | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 10:30 | PASS |  | 2022-04-05 09:37 | 2bfc5a27-53c8-4603-bb8b-361c3cc3be01
9a0ce60c-c61b-4140-9807-c4dbeb401ca8 | Test proiect final | DAN-9 | [Company field] Verify that Company field is mandatory | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 10:30 | PASS |  | 2022-04-05 09:37 | f268dac9-4a18-4dd6-9941-e24dbe0772ff
9a0ce60c-c61b-4140-9807-c4dbeb401ca8 | Test proiect final | DAN-9 | [Company field] Verify that Company field is mandatory | 4 | Fill in all mandatory fields except Company field. |  | All mandatory fields are filled in, except Company field. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 10:30 | PASS |  | 2022-04-05 09:37 | f3c68c6c-5cfe-4e64-88ae-cf6ba3df9e5d
9a0ce60c-c61b-4140-9807-c4dbeb401ca8 | Test proiect final | DAN-9 | [Company field] Verify that Company field is mandatory | 5 | Click Save button. |  | The Work Experience entry was not added. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 10:30 | PASS |  | 2022-04-05 09:37 | 4f73fc47-3823-4354-a2f5-beff95fff895
a3486d3d-4141-42cf-97a7-95f6a80f004a | Test proiect final | DAN-10 | [Company field] Verify that Company field accept any type of characters | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:32 | PASS |  | 2022-04-05 09:37 | dcb6943e-3b59-4a3d-be75-a324fc0dbfbc
a3486d3d-4141-42cf-97a7-95f6a80f004a | Test proiect final | DAN-10 | [Company field] Verify that Company field accept any type of characters | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:32 | PASS |  | 2022-04-05 09:37 | 941d7fbe-06c0-4b9e-b7c8-3dd49d7cd989
a3486d3d-4141-42cf-97a7-95f6a80f004a | Test proiect final | DAN-10 | [Company field] Verify that Company field accept any type of characters | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:32 | PASS |  | 2022-04-05 09:37 | 957c9fda-57c2-4102-8f0f-45a4bc787e18
a3486d3d-4141-42cf-97a7-95f6a80f004a | Test proiect final | DAN-10 | [Company field] Verify that Company field accept any type of characters | 4 | Fill in the Company field with different type of characters as numbers, letters, signs or other special characters. |  | User is allowed to use any type of characters including special ones. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:32 | PASS |  | 2022-04-05 09:37 | 81cce313-4ebc-468f-af23-186baaa6ba7b
60546f74-ba66-4ff0-9037-2ed1329a83af | Test proiect final | DAN-11 | [Company field] Verify that Company field accept maximum 100 characters | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:33 | PASS |  | 2022-04-05 09:37 | df8bfadd-7740-4270-af6d-cb9cc46d3a9c
60546f74-ba66-4ff0-9037-2ed1329a83af | Test proiect final | DAN-11 | [Company field] Verify that Company field accept maximum 100 characters | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:33 | PASS |  | 2022-04-05 09:37 | dee4bd2e-0719-4ebe-b90e-5735a8bb79ff
60546f74-ba66-4ff0-9037-2ed1329a83af | Test proiect final | DAN-11 | [Company field] Verify that Company field accept maximum 100 characters | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:33 | PASS |  | 2022-04-05 09:37 | cc1adc2a-8cef-4130-ae9a-d68b07ad5223
60546f74-ba66-4ff0-9037-2ed1329a83af | Test proiect final | DAN-11 | [Company field] Verify that Company field accept maximum 100 characters | 4 | Fill in the Company field with 101 characters. |  | User is limited to maximum 100 characters. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:33 | PASS |  | 2022-04-05 09:37 | bb78cf97-88b5-4e29-a531-0dbd97277ddc
5f015f40-c25d-471e-9711-67bd317b5894 | Test proiect final | DAN-12 | [Company field] Verify that Company field can be edited | 1 | Precondition: at least one Work Experiences entry added before. |  |  | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:35 | PASS |  | 2022-04-05 09:37 | cd4b576e-6e1c-497f-a525-9edc93f0d18f
5f015f40-c25d-471e-9711-67bd317b5894 | Test proiect final | DAN-12 | [Company field] Verify that Company field can be edited | 2 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:35 | PASS |  | 2022-04-05 09:37 | ffb805b4-f724-4320-810d-77b5ba182dfb
5f015f40-c25d-471e-9711-67bd317b5894 | Test proiect final | DAN-12 | [Company field] Verify that Company field can be edited | 3 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:35 | PASS |  | 2022-04-05 09:37 | 9c69c50b-9323-48f7-85e1-d86b4ae5b05c
5f015f40-c25d-471e-9711-67bd317b5894 | Test proiect final | DAN-12 | [Company field] Verify that Company field can be edited | 4 | Click on the name of the Company you want to change |  | The Work Experience entry is opened successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:35 | PASS |  | 2022-04-05 09:37 | ba57a052-f31c-418c-a55e-85b0deee0d67
5f015f40-c25d-471e-9711-67bd317b5894 | Test proiect final | DAN-12 | [Company field] Verify that Company field can be edited | 5 | Fill the Company field with a new company name. |  | Company field is completed with the new company name. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:35 | PASS |  | 2022-04-05 09:37 | dab0ff10-0b44-43d6-83e0-72db252f98b8
5f015f40-c25d-471e-9711-67bd317b5894 | Test proiect final | DAN-12 | [Company field] Verify that Company field can be edited | 6 | Press Save button. |  | The Work Experience edit form is closed and the Company field is updated successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 10:35 | PASS |  | 2022-04-05 09:37 | e5c112c7-f30b-4f6b-a26f-ba11adb4f0f8
a868531a-b445-4a5c-8837-b505060dbc25 | Test proiect final | DAN-22 | [Comment field] Verify that Comment field accept any type of characters | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:37 | PASS |  | 2022-04-05 09:37 | ccf19f64-0d04-46f5-84fd-b1743465af47
a868531a-b445-4a5c-8837-b505060dbc25 | Test proiect final | DAN-22 | [Comment field] Verify that Comment field accept any type of characters | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:37 | PASS |  | 2022-04-05 09:37 | 0a314584-467e-43b6-8d4a-6712afcf8dc6
a868531a-b445-4a5c-8837-b505060dbc25 | Test proiect final | DAN-22 | [Comment field] Verify that Comment field accept any type of characters | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:37 | PASS |  | 2022-04-05 09:37 | b94e5de2-464f-4794-9db5-393b572a9506
a868531a-b445-4a5c-8837-b505060dbc25 | Test proiect final | DAN-22 | [Comment field] Verify that Comment field accept any type of characters | 4 | Fill in all mandatory fields. |  | All mandatory fields are fill in (Company and Job Title). | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:37 | PASS |  | 2022-04-05 09:37 | f35832f2-f237-435f-9d3a-dec5d0a15178
a868531a-b445-4a5c-8837-b505060dbc25 | Test proiect final | DAN-22 | [Comment field] Verify that Comment field accept any type of characters | 5 | Fill in the Comment field with different type of characters as numbers, letters, signs or other special characters. |  | User is allowed to use any type of characters including special ones. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:37 | PASS |  | 2022-04-05 09:37 | a4422e93-ff6d-45fc-9536-d62ff51393b6
3851526d-a0a4-43e6-ba92-d0bcc5319044 | Test proiect final | DAN-14 | [Job title] Verify that Job Title field accept any type of characters | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:08 | PASS |  | 2022-04-05 09:37 | 52fd17ac-dac4-42ef-94de-7d2a20b83045
3851526d-a0a4-43e6-ba92-d0bcc5319044 | Test proiect final | DAN-14 | [Job title] Verify that Job Title field accept any type of characters | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:08 | PASS |  | 2022-04-05 09:37 | af6094a4-7fdd-4ea8-a1eb-2a8c33916907
3851526d-a0a4-43e6-ba92-d0bcc5319044 | Test proiect final | DAN-14 | [Job title] Verify that Job Title field accept any type of characters | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:08 | PASS |  | 2022-04-05 09:37 | f978f261-3b13-4001-8e72-bbfb70615bf4
3851526d-a0a4-43e6-ba92-d0bcc5319044 | Test proiect final | DAN-14 | [Job title] Verify that Job Title field accept any type of characters | 4 | Fill in the Job Title field with different type of characters as numbers, letters, signs or other special characters. |  | User is allowed to use any type of characters including special ones. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:08 | PASS |  | 2022-04-05 09:37 | f091f207-17d5-4a83-9263-8a5e85d96b1d
8617640d-7b31-4525-8007-a89ac9c48c70 | Test proiect final | DAN-15 | [Job title field] Verify that Job Title field accept accept maximum 100 characters | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:10 | PASS |  | 2022-04-05 09:37 | 57989e43-984c-4f35-9400-3b6bc119cab5
8617640d-7b31-4525-8007-a89ac9c48c70 | Test proiect final | DAN-15 | [Job title field] Verify that Job Title field accept accept maximum 100 characters | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:10 | PASS |  | 2022-04-05 09:37 | f757c8bf-8b3e-40b9-aa27-aecf6909d191
8617640d-7b31-4525-8007-a89ac9c48c70 | Test proiect final | DAN-15 | [Job title field] Verify that Job Title field accept accept maximum 100 characters | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:10 | PASS |  | 2022-04-05 09:37 | 99856514-d7d7-4c78-b5a0-0569d10d2f26
8617640d-7b31-4525-8007-a89ac9c48c70 | Test proiect final | DAN-15 | [Job title field] Verify that Job Title field accept accept maximum 100 characters | 4 | Fill in the Job Title field with 101 characters. |  | User is limited to maximum 100 characters. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:10 | PASS |  | 2022-04-05 09:37 | e3a9e037-232b-41e1-b0db-fb5fd5f6be0b
0813fb6a-ce79-41d1-a457-773c3a524fdb | Test proiect final | DAN-18 | [To field] Verify that To field can be edit | 1 | Precondition: at least one Work Experience entry added, with To field dated. |  |  | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:13 | PASS |  | 2022-04-05 09:37 | 385933f3-ddcf-43a4-b69e-50040259db8e
0813fb6a-ce79-41d1-a457-773c3a524fdb | Test proiect final | DAN-18 | [To field] Verify that To field can be edit | 2 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:13 | PASS |  | 2022-04-05 09:37 | 57dc8f1d-319e-4d8f-b95c-ad6561e64d22
0813fb6a-ce79-41d1-a457-773c3a524fdb | Test proiect final | DAN-18 | [To field] Verify that To field can be edit | 3 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:13 | PASS |  | 2022-04-05 09:37 | 731cd590-8912-46b4-b6a4-c2d66c322d92
0813fb6a-ce79-41d1-a457-773c3a524fdb | Test proiect final | DAN-18 | [To field] Verify that To field can be edit | 4 | Click on the name of the Company you want to change. |  | The Work Experience entry is opened successfully. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:13 | PASS |  | 2022-04-05 09:37 | a42201d0-e745-47e6-914b-d3e112cda7ed
0813fb6a-ce79-41d1-a457-773c3a524fdb | Test proiect final | DAN-18 | [To field] Verify that To field can be edit | 5 | Change date for To field with a different value and press Save button. |  | To field is editable and the new date is saved successfully. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:13 | PASS |  | 2022-04-05 09:37 | ab185f22-b270-4f73-8d26-337452969e1b
f26e9040-3171-4d09-a974-ae4174d472af | Test proiect final | DAN-19 | [From field] Verify that From and To fields accept only dd-mm-yyyy format | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:22 | FAIL | DAN-25 | 2022-04-05 09:37 | 3181c713-031c-454b-b3a7-c85e27309ca5
f26e9040-3171-4d09-a974-ae4174d472af | Test proiect final | DAN-19 | [From field] Verify that From and To fields accept only dd-mm-yyyy format | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:22 | FAIL | DAN-25 | 2022-04-05 09:37 | b5c7827d-f783-4bfd-94ff-6054e0910cda
f26e9040-3171-4d09-a974-ae4174d472af | Test proiect final | DAN-19 | [From field] Verify that From and To fields accept only dd-mm-yyyy format | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:22 | FAIL | DAN-25 | 2022-04-05 09:37 | d9ef568b-ff6e-4471-b863-4a0272ffaa07
f26e9040-3171-4d09-a974-ae4174d472af | Test proiect final | DAN-19 | [From field] Verify that From and To fields accept only dd-mm-yyyy format | 4 | Fill in all mandatory fields. |  | All mandatory fields are fill in (Company and Job Title). | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:22 | FAIL | DAN-25 | 2022-04-05 09:37 | dac3d559-8849-4ba6-b3d4-147c7b25e418
f26e9040-3171-4d09-a974-ae4174d472af | Test proiect final | DAN-19 | [From field] Verify that From and To fields accept only dd-mm-yyyy format | 5 | For From and To fields type characters. |  | From and To fields should not allow any character. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:22 | FAIL | DAN-25 | 2022-04-05 09:37 | e44b586f-c8ac-450a-935b-3cd3ce50a9ec
f26e9040-3171-4d09-a974-ae4174d472af | Test proiect final | DAN-19 | [From field] Verify that From and To fields accept only dd-mm-yyyy format | 6 | For From and To fields type a date with the format in reverse yyyy-mm-dd. |  | Typed format should not be allowed. | FAIL | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:22 | FAIL | DAN-25 | 2022-04-05 09:37 | 21ad44fd-b70a-456a-96c6-9678b3faa767
f26e9040-3171-4d09-a974-ae4174d472af | Test proiect final | DAN-19 | [From field] Verify that From and To fields accept only dd-mm-yyyy format | 7 | For From and To field select calendar icon and choose a date from past. |  | The selected date is fill in with format dd-mm-yyyy. | FAIL | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:22 | FAIL | DAN-25 | 2022-04-05 09:37 | 3b595672-f4fb-48e7-b1af-84a86e06cb89
f26e9040-3171-4d09-a974-ae4174d472af | Test proiect final | DAN-19 | [From field] Verify that From and To fields accept only dd-mm-yyyy format | 8 | Press Save button. |  | The Work Experience entry is successfully added. | UNEXECUTED | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:22 | FAIL | DAN-25 | 2022-04-05 09:37 | 817feea0-a097-481c-8078-76d142187501
4c86c5ae-60e7-4883-9b55-6c5961206aa2 | Test proiect final | DAN-21 | [To field] Verify that To date field should be after From date field | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:36 | PASS |  | 2022-04-05 09:37 | 93173307-1dbf-4d55-ac7a-59fdf92c1d61
4c86c5ae-60e7-4883-9b55-6c5961206aa2 | Test proiect final | DAN-21 | [To field] Verify that To date field should be after From date field | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:36 | PASS |  | 2022-04-05 09:37 | cf54dc90-ed93-431b-91de-0a68bfb2c57a
4c86c5ae-60e7-4883-9b55-6c5961206aa2 | Test proiect final | DAN-21 | [To field] Verify that To date field should be after From date field | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:36 | PASS |  | 2022-04-05 09:37 | 1fb08689-bcf5-4a33-853c-ff68bc414493
4c86c5ae-60e7-4883-9b55-6c5961206aa2 | Test proiect final | DAN-21 | [To field] Verify that To date field should be after From date field | 4 | Fill in all mandatory fields. |  | All mandatory fields are fill in (Company and Job Title). | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:36 | PASS |  | 2022-04-05 09:37 | a1f8129a-59f7-4b53-a62b-56d55c44df4e
4c86c5ae-60e7-4883-9b55-6c5961206aa2 | Test proiect final | DAN-21 | [To field] Verify that To date field should be after From date field | 5 | For From field select calendar icon and choose a date from past.(for exemple 10-02-2020) |  | The selected date is fill in with format dd-mm-yyyy. | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:36 | PASS |  | 2022-04-05 09:37 | 7f55ec65-3176-48a9-8747-c84115d74dd1
4c86c5ae-60e7-4883-9b55-6c5961206aa2 | Test proiect final | DAN-21 | [To field] Verify that To date field should be after From date field | 6 | For To field select calendar icon and choose a date before the From field date and press Save Button.(for exemple 10-02-2010) |  | The entry can't be saved and the message that should appear is:"To date should be after From date". | PASS | DanielaTuia | Low | TestareManuala2 | 2022-06-05 12:36 | PASS |  | 2022-04-05 09:37 | fbdaf582-76a1-4f77-933d-7e03a9ec5fc8
74121e69-8c46-4f2b-bb3f-f052db14887b | Test proiect final | DAN-13 | [Job Title field] Verify that Job Title field is mandatory | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:06 | PASS |  | 2022-04-05 09:37 | fac54c92-fbb1-415c-8f46-2f0d04a71ae8
74121e69-8c46-4f2b-bb3f-f052db14887b | Test proiect final | DAN-13 | [Job Title field] Verify that Job Title field is mandatory | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:06 | PASS |  | 2022-04-05 09:37 | 82c36367-0ca3-4676-a306-88751a7c22f9
74121e69-8c46-4f2b-bb3f-f052db14887b | Test proiect final | DAN-13 | [Job Title field] Verify that Job Title field is mandatory | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:06 | PASS |  | 2022-04-05 09:37 | 3a7b76bc-bffe-43d6-9d7a-5aceae26b324
74121e69-8c46-4f2b-bb3f-f052db14887b | Test proiect final | DAN-13 | [Job Title field] Verify that Job Title field is mandatory | 4 | Fill in all mandatory fields except Job Title field. |  | All mandatory fields are filled in, except Job Title field. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:06 | PASS |  | 2022-04-05 09:37 | 0d365d7d-038f-4a1e-b775-5d9ea0c9e5ca
74121e69-8c46-4f2b-bb3f-f052db14887b | Test proiect final | DAN-13 | [Job Title field] Verify that Job Title field is mandatory | 5 | Click Save button. |  | The Work Experience entry was not added. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:06 | PASS |  | 2022-04-05 09:37 | 34a5e311-2dba-4578-a9f4-575309a9530d
0a7d46f0-30c1-4eb7-9b48-1c9a9c9ae7f7 | Test proiect final | DAN-16 | [Job title field] Verify that Job Title field can be edited | 1 | Precondition: at least one Work Experiences entry added before. |  |  | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:11 | PASS |  | 2022-04-05 09:37 | bde951d5-1f9f-4ba5-b81e-879f81000a61
0a7d46f0-30c1-4eb7-9b48-1c9a9c9ae7f7 | Test proiect final | DAN-16 | [Job title field] Verify that Job Title field can be edited | 2 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:11 | PASS |  | 2022-04-05 09:37 | a597daf8-d2de-487a-87e7-38bc8f609fbc
0a7d46f0-30c1-4eb7-9b48-1c9a9c9ae7f7 | Test proiect final | DAN-16 | [Job title field] Verify that Job Title field can be edited | 3 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:11 | PASS |  | 2022-04-05 09:37 | 446afe1c-d82b-4bef-9263-d84838b58bb9
0a7d46f0-30c1-4eb7-9b48-1c9a9c9ae7f7 | Test proiect final | DAN-16 | [Job title field] Verify that Job Title field can be edited | 4 | Click on the name of the Company you want to change |  | The Work Experience entry is opened successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:11 | PASS |  | 2022-04-05 09:37 | 60f6e206-0c5f-430a-9231-a3f8c8a4fd2e
0a7d46f0-30c1-4eb7-9b48-1c9a9c9ae7f7 | Test proiect final | DAN-16 | [Job title field] Verify that Job Title field can be edited | 5 | Fill the Job Title field with a new Job Title name. |  | Job Title field is completed with the new Job Title name. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:11 | PASS |  | 2022-04-05 09:37 | 4c85ac0e-c9c5-4dfe-a5e8-01db1a9b7e57
0a7d46f0-30c1-4eb7-9b48-1c9a9c9ae7f7 | Test proiect final | DAN-16 | [Job title field] Verify that Job Title field can be edited | 6 | Press Save button. |  | The Work Experience edit form is closed and the Job Title field is updated successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 11:11 | PASS |  | 2022-04-05 09:37 | fe25a1f6-b1b5-4f54-8575-250947a47f70
1da962ff-d734-472e-9819-05582fcc6204 | Test proiect final | DAN-17 | [From field] Verify that From field can be edit | 1 | Precondition: at least one Work Experience entry added, with From field dated. |  |  | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:12 | PASS |  | 2022-04-05 09:37 | bb550de0-b86a-48c9-9567-af31ad15d4d8
1da962ff-d734-472e-9819-05582fcc6204 | Test proiect final | DAN-17 | [From field] Verify that From field can be edit | 2 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:12 | PASS |  | 2022-04-05 09:37 | 620f5bfd-729f-41a9-945c-adff79323784
1da962ff-d734-472e-9819-05582fcc6204 | Test proiect final | DAN-17 | [From field] Verify that From field can be edit | 3 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:12 | PASS |  | 2022-04-05 09:37 | 235b5210-b355-4c11-9f1f-f0e3142bc8ac
1da962ff-d734-472e-9819-05582fcc6204 | Test proiect final | DAN-17 | [From field] Verify that From field can be edit | 4 | Click on the name of the Company you want to change. |  | The Work Experience entry is opened successfully. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:12 | PASS |  | 2022-04-05 09:37 | a8412f1f-89ba-4cfc-b8ed-62c60e44e506
1da962ff-d734-472e-9819-05582fcc6204 | Test proiect final | DAN-17 | [From field] Verify that From field can be edit | 5 | Change date for From field with a different value and press Save button. |  | From field is editable and the new date is saved successfully. | PASS | DanielaTuia | High | TestareManuala2 | 2022-06-05 11:12 | PASS |  | 2022-04-05 09:37 | d26bc3e5-9e0b-4450-9f46-3eb0c28bdc5e
e75a7fb1-4c9e-40a5-9038-0648e3a2f411 | Test proiect final | DAN-20 | [Save button] Verify that user can't save action when From and To fields input is a future date | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:08 | FAIL | DAN-26 | 2022-04-05 09:37 | 0b510350-53cb-4bc0-9f58-4aab8036054e
e75a7fb1-4c9e-40a5-9038-0648e3a2f411 | Test proiect final | DAN-20 | [Save button] Verify that user can't save action when From and To fields input is a future date | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:08 | FAIL | DAN-26 | 2022-04-05 09:37 | fa80c3ea-8d80-4982-875b-cfd8960aab38
e75a7fb1-4c9e-40a5-9038-0648e3a2f411 | Test proiect final | DAN-20 | [Save button] Verify that user can't save action when From and To fields input is a future date | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:08 | FAIL | DAN-26 | 2022-04-05 09:37 | 1c235c3b-4a45-44aa-98ef-6cf9780fabe5
e75a7fb1-4c9e-40a5-9038-0648e3a2f411 | Test proiect final | DAN-20 | [Save button] Verify that user can't save action when From and To fields input is a future date | 4 | Fill in all mandatory fields. |  | All mandatory fields are fill in (Company and Job Title). | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:08 | FAIL | DAN-26 | 2022-04-05 09:37 | 12b05cee-f3d2-4aeb-88ee-487f42787391
e75a7fb1-4c9e-40a5-9038-0648e3a2f411 | Test proiect final | DAN-20 | [Save button] Verify that user can't save action when From and To fields input is a future date | 5 | For From and To field select calendar icon and choose a date from future. |  | Future date should not be allowed to be selected. | FAIL | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:08 | FAIL | DAN-26 | 2022-04-05 09:37 | 9aa21349-f5a2-4381-a90b-ef410759b605
e75a7fb1-4c9e-40a5-9038-0648e3a2f411 | Test proiect final | DAN-20 | [Save button] Verify that user can't save action when From and To fields input is a future date | 6 | Leave Form and To field empty or choose a date from past and press Save Button. |  | The Work Experience entry is successfully added. | UNEXECUTED | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:08 | FAIL | DAN-26 | 2022-04-05 09:37 | c9abbb28-2ef8-4d48-a1c7-3149d1b97826
9cb13dfd-eb15-48cb-be70-0fcc12d8eaae | Test proiect final | DAN-23 | [ Comment filed] Verify that Comment field accept maximum 200 characters | 1 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:38 | PASS |  | 2022-04-05 09:37 | aaf2c0e7-d28b-40e4-aa86-27c405982601
9cb13dfd-eb15-48cb-be70-0fcc12d8eaae | Test proiect final | DAN-23 | [ Comment filed] Verify that Comment field accept maximum 200 characters | 2 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:38 | PASS |  | 2022-04-05 09:37 | 8ab50b0a-ab81-46b3-8ae5-3796436f62a7
9cb13dfd-eb15-48cb-be70-0fcc12d8eaae | Test proiect final | DAN-23 | [ Comment filed] Verify that Comment field accept maximum 200 characters | 3 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:38 | PASS |  | 2022-04-05 09:37 | 34beea8e-ab1c-4380-a896-81d00962976d
9cb13dfd-eb15-48cb-be70-0fcc12d8eaae | Test proiect final | DAN-23 | [ Comment filed] Verify that Comment field accept maximum 200 characters | 4 | Fill in all mandatory fields. |  | All mandatory fields are fill in (Company and Job Title). | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:38 | PASS |  | 2022-04-05 09:37 | 4a39d66c-6c7a-4e81-9bd7-83907c6aeae9
9cb13dfd-eb15-48cb-be70-0fcc12d8eaae | Test proiect final | DAN-23 | [ Comment filed] Verify that Comment field accept maximum 200 characters | 5 | Fill in the Comment field with 201 characters. |  | User is limited to maximum 200 characters. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:38 | PASS |  | 2022-04-05 09:37 | b2754c18-bfc1-417a-9fd4-28aaec2a455a
f9f3df86-aace-4ece-8b42-a301c8ace77c | Test proiect final | DAN-24 | [Comment field] Verify that Comment field can be edited | 1 | Precondition: at least one Work Experiences entry added before with the Comment field filled in. |  |  | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:39 | PASS |  | 2022-04-05 09:37 | 6ce68731-db54-4039-bdb6-ed25024f44d8
f9f3df86-aace-4ece-8b42-a301c8ace77c | Test proiect final | DAN-24 | [Comment field] Verify that Comment field can be edited | 2 | Login to Orange HRM. |  | The user can successfully login into the application. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:39 | PASS |  | 2022-04-05 09:37 | eda1ae2d-2318-4bda-b345-02a5ecefed1b
f9f3df86-aace-4ece-8b42-a301c8ace77c | Test proiect final | DAN-24 | [Comment field] Verify that Comment field can be edited | 3 | Access My Info module and open the Qualifications section. |  | My Info module is visibile to the end user and the Qualifications section is opened. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:39 | PASS |  | 2022-04-05 09:37 | 57f74f65-a279-4840-97f7-27c7e9f0aa47
f9f3df86-aace-4ece-8b42-a301c8ace77c | Test proiect final | DAN-24 | [Comment field] Verify that Comment field can be edited | 4 | Acces Work Experience section by clicking Add button. |  | The Add Work Experience section is shown. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:39 | PASS |  | 2022-04-05 09:37 | 88001181-d162-46e2-a160-a46b849ce6f4
f9f3df86-aace-4ece-8b42-a301c8ace77c | Test proiect final | DAN-24 | [Comment field] Verify that Comment field can be edited | 5 | Click on the name of the Company were you want to update information. |  | The Work Experience entry is opened successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:39 | PASS |  | 2022-04-05 09:37 | e092ec7d-d3dd-40fe-a0cb-9f9aa1c3330f
f9f3df86-aace-4ece-8b42-a301c8ace77c | Test proiect final | DAN-24 | [Comment field] Verify that Comment field can be edited | 6 | Fill the Comment field with new information. |  | Comment field is completed with the new information. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:39 | PASS |  | 2022-04-05 09:37 | 87e3837e-0644-4b6b-8272-995eebfb42d7
f9f3df86-aace-4ece-8b42-a301c8ace77c | Test proiect final | DAN-24 | [Comment field] Verify that Comment field can be edited | 7 | Press Save button. |  | The Work Experience edit form is closed and the Comment field is updated successfully. | PASS | DanielaTuia | Medium | TestareManuala2 | 2022-06-05 12:39 | PASS |  | 2022-04-05 09:37 | 5320f413-5c35-4012-a32b-6d8751a93a07